## Overview - Read Me
This RACI Matrix will assist customers to determine which organization functions (internal or external) will be involved (i.e. responsible, accountable, consulted, informed) while migrating to and/or operating in the cloud. Different IT functions are listed in Column A under key categories/headings. Three high level phases are assumed: - Current State - the existing on prem environment with little to no cloud presence - Transition State - the interim state where part of the IT environment will be on cloud and part will remain on prem - Future State - the final state where the majority of the IT environment will be in the cloud and a small presence will remain on prem. This RACI Matrix was created for an organization employing a federal-state IT Operating model. Row 4 has five separate teams listed: - Shared Services - manages the Infrastructure, Security and Network (in this specific scenario). - Business Units (BUs) - responsible for managing applications. - AWS - refers to the AWS platform and associated support services - AWS AT - refers to the AWS Account Team (Account Manager, Solutions Architect, Technical Account Manager, Professional Services, Conceirge) - SaaS - Software as a Service providers the customer may be using Note: Not all functions will be applicable for each customer and will need to be customized and the IT organization model will need to be updated based on the customer's current or desired state (e.g. fully centralized, fully decentralized).

## RACI Matrix
R - Responsible | RACI Matrix
A - Accountable
C - Consulted | Current State | [5 empty] | Transition State | [5 empty] | Future State
I - Informed | Shd Svc | BU | AWS* | AWS AT** | Partner | SaaS | Shd Svc | BU | AWS* | AWS AT** | Partner | SaaS | Shd Svc | BU | AWS* | AWS AT** | Partner | SaaS
Architecture:
- Infrastructure Architecture
- Network Architecture
- Security Architecture
- Data Architecture
- Application Implementation Architecture
- Application Migration Patterns
- Cloud Design Principles and Patterns
Technical Compliance:
- Standards and Controls
- System Provisioning
- Consumption/Capacity Management
- Vendor Management
- Release Management
- Configuration & Change Management
- Environment Management
- Application Versioning
- AMI Versioning (Golden Images)
- Application HA / Resilience
- Application DR / Backups
- SLA Strategy
- Business Continuity Planning
Monitoring and Reporting:
- Application Monitoring
- AWS Monitoring and Support
- Log and Event Monitoring
- Hardware Monitoring
- Connectivity Monitoring (ext. partners)
- Security Logging and Monitoring
- DR Incident Management
Network
- Network Architecture
- Network Security Validation
- VPN Access
- (Direct) Connectivity
Security
- Security Architecture
- Security and Compliance Validation
- Application Security Validation
- Virus Scanning
- Vulnerability Scanning
- Application Security Scanning
- Firewall Services
- Identity and Access Management / Logical Access
- Data Encryption
- Security Logging & Monitoring
- Security Incident Response
- Security Operations Playbook
Finance
- Financial Management
- Capacity Planning and Forecasting
- Billing & Account Management
- Asset Management
Operations:
- Custom Maintenance Windows
- O/S Updates and Security Patching
- Custom Restarts and Escalation Procedures
- Data Backups and Restores
- DNS Management
- Release Automation
- Hardware Builds
- System Hardening
- Run Book Documentation
- Incident Management
- Problem Management
- Change Management
- Release & Deployment Management
People Management
- Org Structures
- Roles and Job Descriptions
- Skills and Competencies
- Trainings & Certifications
- Compensation
- Org Change Management
Business Management
- Cloud Strategy
- Budget & Cost Management
- Supplier Management
- Risk Management
- Benefit Management
- Product Management
- M&A
- Client Management
* AWS refers to the AWS technology platform (i.e. infrastructure, network) and AWS Support
**AWS AT refers to the AWS Account Team supporting Customer (e.g. Account Manager, Solutions Architect, Professional Services, Technical Account Managers, Concierge Team)