## Readme
RACI Nomenclature |  | Advice for Delivering Consultants
R - Responsible | Person working on activity
A - Accountable | Person with decision authority
C - Consulted | Stakeholder who should be contributing to the decision or activity
I - Informed | Has a need to know about the decision or activity
Team Definition:
The ProServe Global Migrations Practice will include a series of persistent and dedicated resources (Migration Success Managers, Migration Technical Leads) to lead projects end-to-end. These resources together will define a consistent process and set of methods to accelerate customer migration projects and drive scale. This team will own and optimize the process, harvest lessons learned as we progress, cultivate partner capacity, and drive education and consistency in delivery migration projects for the customer. This version of the matrix was designed with the position that the Migration Planning Project is being lead by AWS, in conjunction with a partner. Alterations will need to be made for Partner or Customer lead engagements.
AWS - Prime
Version | Date
v1.0
v1.1

## CCoE RACI
R - Responsible | CoE
A - Accountable
C - Consulted
I - Informed
Domains → | Steering / Cloud Governance & Performance Committee |  |  | PMO |  | Helpdesk/Service Desk and Support | Cloud Infrastructure |  |  | DevOps and Automation |  | Cloud Architecture(s) |  | Security, Risk & Compliance
Roles → | Chief Cloud Officer / CTO | Executive Leadership | Executive Sponsor | PMO Lead | Business Relationship Manager | Helpdesk Lead | Cloud Infrastructure Lead | Enterprise Cloud Engineer | Enterprise Operations Engineers | DevOps and Automation Lead | DevOps Engineer | Application Lead(s) | Cloud Migration Engineer | Security, Risk & Compliance Lead | Security Engineer
Migration:
Application Portfolio Discovery
Application Analysis
Storage and Database Analysis
Migration Design
Migration Factory
Operations and Optimization
Architecture:
Infrastructure Architecture
Network Connectivity Architecture
Application Implementation Architecture
Cloud Design Principles and Patterns
Disaster Recovery/BCP
Technical Compliance:
- Release Management
- Configuration & Change Management
- Application Versioning
- Security and Compliance Validation
- OS Compliance
Monitoring and Reporting:
- Application Monitoring
- Log and Event Monitoring
- Infrastructure Monitoring
- Connectivity Monitoring (ext. partners)
- Security Logging and Monitoring
Security
- Application Security Validation
- Virus/Malware Detection
- Vulnerability Scanning
- Application Security Scanning
- Firewall Services
- Identity and Access Management / Logical Access
- Data Encryption
- Security Incident Response
- Security Operations Playbook
- Data Forensics
- Security Patching
Operations:
- O/S Hardening and Patching
- Data Backups and Restores
- DNS Management
- Release Automation
- Run Book Documentation
- Incident Management
- Problem Management
- Change Management
- Release & Deployment Management
Governance
- Org Structures
- Roles and Responsibilities
- Skills and Competencies
- Trainings & Certifications
- AWS Account Structure
- Billing & Account Management
- Asset Management

## Example Customer_Partner_PS
Role | Responsibility | AWS | Customer | Partner | Responsible | Second Responsible | Accountable | Consulted | Informed | Facilitator
Migration Success Manager | Manage the project end to end and will be responsible for aligning the expectations of various stakeholders from customers and partners, keeping everyone accountable to their commitments, and limit the impact of competing agendas and politics with clear and timely communication and repeatable project plans.
Migration Technical Lead | Responsible for decision making and architecture design for individual teams. Provides depth in cloud expertise as well as familiarity with application migration methodology for effectiveness at the team level.
AWS Subject Matter Experts | Specialty resource assignments (Security, Infrastructure Architecture, DevOps, Application Development, and Database) skill sets based on a pooled model are based on the scheduled needs of the project and will be coordinated by the Migration Success Manager.
Cloud Migration Leader | Provides Executive leadership and direction to the project. Evaluates cloud technological developments and evolving business requirements. Provides high-level specialized technical support and consultation to business lines.
Project Manager | As a key member of the Project Control Team, the PM will Plan, budget, oversee and document all aspects of the planning project. The customer Project Manager will work closely with upper management and the MSM to make sure that the scope and direction of the project is on schedule, as well as other departments for support.
Portfolio Discovery and Planning Team | Review data, tools, application patterns, and requirements provided by the Customer and determine if the dataset's are complete enough to build a plan for migration. Build and document recommendations and plans for the initial migration wave.
Operations Integration Team | Builds the plan of the appropriate foundational components that ensure landing zone environments are scalable and appropriately maintained and monitored. Supportability, licence consolidation and contracts, data center lease expiration. Focus on the tobe. Workforce transition. I've migrated now how do I supprt and run this. Application lifecycle management.
Migration Team | Develop and plan the first wave migration’s of a small number of applications in advance of a completed overall migration plan developed by the other teams.
TCO | Conducts financial analysis and tradeoff studies for cost optimization options.
Cloud Foundations Team
Role | Responsibility | AWS | Customer | Partner | Responsible | Second Responsible | Accountable | Consulted | Informed | Facilitator
Cloud Business Owner or Sponsor | Define, review and implement cloud operational policies and procedures. Establish the company vision and strategy for Cloud services and lead all aspects of development in these areas. Leverage the cloud for competitive advantage and align existing lines of business with cloud initiatives. Manage cloud vendor relationships. Monitor and report cloud effectiveness performance. Define and own cloud SLAs for business units. Ensure cloud compliance with business regulations.
PMO | Drive standard project methodology and engender the culture of process excellence across the organization. Manage projects from initiation to project close, meeting all project objectives such as compliance, cost savings, process improvement / redesign within the agreed timelines. Drive projects to fruition with highly collaborative relationships across functions and geographies ensuring that the project vision and goals are clearly communicated with the identified key stakeholders. Lead and coordinate requirement-gathering workshops with internal customers and stakeholders to develop new policies and process flows. Coordinate and participate in user acceptance testing and subsequent issue resolution. Provide status updates and reviews in line with agreed milestones. Manage project risks, issues, exceptions and escalations Continuously improve project delivery and project quality to ensure positive customer satisfaction within and outside of the organization. Identify and implement ongoing efficiency opportunities in end-to-end business processes.
Application Lead | Maintain relationship with business units. Identify service requirements from business. Educate business on services offered by cloud Cloud Foundations Team and how best to leverage the services for improved business performance. Responsible for customer satisfaction and periodically surveying service satisfaction level. Manage customer complaints and involve appropriate teams to respond to customer complaints Identify opportunities for operational efficiencies.
Cloud Infrastructure Lead | Provide 24 X 7 operations for Cloud Services including Disaster Recovery, Scanning and Archiving, Data Repository, and Remote Operations Services. Develop and oversee Network Operations, Service Desk, Event Management, Incident, Management, Problem Management, Configuration Management and Change, Management Processes for all Cloud Services. Ensure successful backup and/or replication of Customer Data in a secure manner. Contribute and enhance Security policies and procedures for AWS Cloud Services. Implement System Management Tools to provide monitoring and management of all AWS Cloud infrastructure. Define and report Key Performance Indicators to monitor process health; define and report Customer facing service metrics. Implement and oversee Security policy, monitoring, guidelines for Cloud Services. Conduct System Outage Analysis to prevent the reoccurrence of incidents.
Cloud Engineer | Maintain and monitor all AWS network, security and other services to meet the organization's current and future requirements. Responsible for management, maintenance and architecture of AWS platform and environment. Monitor systems and identify performance issues proactively. Work within strict time frames and elevate incidents within defined timeframes. Test all changes to networks, AWS services and hosted applications. Monitors service delivery compliance to budget, quality standards and business stakeholder requirements. Cater to doing infrastructure coordination related to design and setup activities at different stages of a project. Work with cloud service providers to ensure productive environment
Security Lead | Provide oversight to client services in delivering technical projects. Use proven security skills to build upon information technology risk, security and privacy work. . Lead the security reviews/audits to ensure compliance. Communicate technical issues by translating technical information. Oversee the work of team members to ensure quality best practices. Leverage industry and technical expertise to assist management to effectively address IT risks associated with their business. Design and coordinate cohesive responses to security events that involve multiple teams across the organization. Build security utilities and tools for internal use that enable to operate at high speed and wide scale. Evaluate the impact to the organization of current security advisories, publications, and academic research papers. Organize responses as necessary across affected teams to do the right thing for our customers and our organization. Recognize, adopt, and instill the best practices in security engineering fields throughout the organization: development, cryptography, network security, security operations, and incident response. Provide subject matter expertise on architecture, authentication and system security. Conduct sophisticated security reviews - from high level web application architecture to OS level parameters in order to meet security goals.
Architecture Lead | Provide thought leadership on creating solution based on AWS, IaaS and PaaS. Have deep understanding of AWS services. Great communication skills and can clearly articulate architecture to peers Design and build scalable, available and secure architecture for products/applications. Compile, develop, and deliver architectural guardrails; influence stakeholders and ensure compliance with architectural guardrails within many technology domains that support the needs of products teams to reliably launch products and services. Drive the evolution of infrastructure, processes, products, and services by convincing decision makers
DevOps Engineers | Responsible for effective provisioning, installation/configuration, automation operation, and maintenance of AWS cloud infrastructure. Design, build and scale infrastructure solutions for products. Manage multiple projects, establish project goals and milestones, and track necessary resources and progress across teams. Communicate issues, goals and milestones effectively.
Cloud Governance Board | Develops an operating charter formalizing these roles and responsibilities. Develop and maintains a set of project “Vision and Goals”. Develops program policy. Obtains support/agreement from stakeholders. Provide effective governance and strategic direction for the initiative. Track the initiative financials to mitigate cost overruns and approve new funding requests. Champions business and technical process improvements. Approve, reject or inquire about additional scope, resource, budget change management